## Sheet1
ID | Title | Description | Root Cause
1 | Incorrect Climate Class for Water Ingress Protection | The train was specified with IPX4 water ingress protection, but the actual requirement was IPX6 due to regional weather conditions. | Misinterpretation of the environmental specification during the bid phase.
2 | Wrong Brake Type Installed | The delivered trainsets were equipped with disc brakes instead of the required tread brakes. | Customer specification was ambiguous, and the engineering team followed the default platform configuration.
3 | Fire Protection Standard Misinterpreted | The design followed EN 45545-2 HL2, but the customer required HL3 for certain materials. | Outdated reference document used during the requirement analysis.
4 | Incorrect Door Width | Passenger doors were designed at 1,200 mm instead of the required 1,300 mm. | Mismatch between the customer’s latest specification and the version used in the bid.
5 | Non-Compliant HVAC System | The HVAC system did not meet the required temperature range for desert operation. | Climatic zone was incorrectly classified as temperate instead of arid.
6 | Incompatible Coupling Interface | The train was delivered with a Scharfenberg coupler, while the customer required a Dellner type. | Copy-paste error from a previous project’s specification.
7 | Insufficient EMC Shielding | The train’s communication system experienced interference due to inadequate EMC shielding. | Missing update in the EMC requirement list during the design freeze.
8 | Incorrect Pantograph Type | A single-arm pantograph was installed, but the infrastructure required a double-arm type. | Lack of coordination between infrastructure compatibility checks and procurement.
9 | Wrong Interior Layout for Accessibility | The train did not include the required number of wheelchair spaces. | Accessibility standards were updated after the bid submission and the requirement was overlooked.
10 | Non-Compliant Paint System | The exterior paint failed salt spray tests required for coastal operation. | Used a standard paint system without verifying environmental durability requirements.